## Sheet1
Defect Id | Defect Description | Version | Steps | Date Raised | Reference | Detected By | Status | Fixed by | Date Closed | Severity | Priority
1 | Timer functionality allows user to unblock before time expires |  |  | 20th March |  | Project Manager | Defect fixed | Developer | 2015-04-01 | Serious | High
2 | Profile feature does not save the selected applications |  |  | 2015-04-04 |  | Tester | Defect fixed | Developer | 2015-04-06 | Medium | Medium
3 | Sms Alert does not reach master on deactivation if profile changed |  |  | 2015-04-16 |  | Tester | Defect fixed | Deveoper | 2015-04-18 | Medium | Medium